## Gantt Chart w % Complete
| TASK NAME | START DATE | DAY OF MONTH | END DATE | DURATION (WORK DAYS) | DAYS COMPLETE | DAYS REMAINING | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Data Mining Project
| Normalization | 2018-10-01 | 1 | 2018-10-04 | 3 | 0 | 3 | Michael/Chris | 0%
| Feature Selection | 2018-10-03 | 3 | 2018-10-07 | 4 | 0 | 4 | Chris/Chen | 0%
| Data Selection | 2018-10-06 | 6 | 2018-10-10 | 4 | 0 | 4 | Thomas | 0%
| Implementation | 2018-10-09 | 9 | 2018-10-20 | 11 | 0 | 11 | Everyone | 0%
| Validation | 2018-10-15 | 15 | 2018-10-20 | 5 | 0 | 5 | Chen/Michael | 0%
| Presentation Preparation | 2018-10-18 | 18 | 2018-10-24 | 6 | 0 | 6 | Everyone | 0%
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS)
Data Mining Project
| Normalization | 2018-10-01 | 2018-10-04 | 0
| Feature Selection | 2018-10-03 | 2018-10-07 | 4
| Data Selection | 2018-10-06 | 2018-10-10 | 4
| Implementation | 2018-10-09 | 2018-10-20 | 11
| Validation | 2018-10-13 | 2018-10-15 | 2
| Confusion Matrix | 2018-10-14 | 2018-10-18 | 4
| Accuracy Plot | 2018-10-17 | 2018-10-20 | 3
| Presentation Preparation | 2018-10-18 | 2018-10-24 | 6
Formulas:
END DATE = [START DATE]+3
START DATE = [END DATE, row above]-1
START DATE = [DAY OF MONTH, row above]-1
DAY OF MONTH = [START DATE]+3

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 3 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 5 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 4 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 3 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 3 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 5 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 9 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 3 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 5 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 5 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 4 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 5 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 3 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 5 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 4 | Rachel | 40%

## Sheet1
| TASK NAME | DURATION | TEAM MEMBER
| Normalization | 3 | Michael & Chris
| Feature Selection | 4 | Chris & Chen
| Data Selection | 4 | Thomas
| Implementation | 11 | Everyone
| Validation | 5 | Chen & Michael
| Presentation Preparation | 6 | Everyone
| TASK NAME | DURATION | TEAM MEMBER
| Normalization | 3 | Michael/Chris
| Feature Selection | 4 | Chris/Chen
| Data Selection | 4 | Thomas
| Implementation | 11 | Everyone
| Validation | 5 | Chen/Michael
| Presentation Preparation | 6 | Everyone
| TASK NAME | START DATE | DAY OF MONTH | END DATE | DURATION (WORK DAYS) | DAYS COMPLETE | DAYS REMAINING | TEAM MEMBER
Data Mining Project
| Normalization | 2018-10-01 | 1 | 2018-10-04 | 3 | 0 | 3 | Michael/Chris
| Feature Selection | 2018-10-03 | 3 | 2018-10-07 | 4 | 0 | 4 | Chris/Chen
| Data Selection | 2018-10-06 | 6 | 2018-10-10 | 4 | 0 | 4 | Thomas
| Implementation | 2018-10-09 | 9 | 2018-10-20 | 11 | 0 | 11 | Everyone
| Validation | 2018-10-15 | 15 | 2018-10-20 | 5 | 0 | 5 | Chen/Michael
| Presentation Preparation | 2018-10-18 | 18 | 2018-10-24 | 6 | 0 | 6 | Everyone
| TASK NAME | DURATION | TEAM MEMBER
| Normalization | 3 | Michael & Chris
| Feature Selection | 4 | Chris & Chen
| Data Selection |  | Thomas
| Implementation |  | Everyone
| Validation |  | Chen & Michael
| Presentation Preparation |  | Everyone
Formulas:
END DATE = [DURATION]+3
DURATION = [END DATE, row above]-1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 3 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 3 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 5 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 5 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 3 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 7 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 4 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 1 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 4 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 3 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 3 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 9 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 5 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 6 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 1 | Rachel | 0%